## Sheet1
Andrea Yoss
Capstone Project Plan |  |  | Key: |  | External Deadline
In Progress
Internal Deadline
|  | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
Task | Additional Details | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13
Capstone Progress Report | https://docs.google.com/forms/d/e/1FAIpQLScxQy0tn6NNJ6dOpZjkby8W7MuVW40baIEcXmy1FHEZBKmIGA/viewform | bar: 2020-03-03
Capstone Check in #3 | progress report and preliminary findings; https://git.generalassemb.ly/DSI-US-10/capstone/tree/master/part_03 | bar: 2020-03-04
Capstone Check in #4 | Report writeup and technical analysis; https://git.generalassemb.ly/DSI-US-10/capstone/tree/master/part_04 | bar: 2020-03-10
Final Repo Due | bar: 2020-03-11
Capstone Presentation | bar: 2020-03-13
Initial "Baseline" Model | Univariate time series model on daily price. | bar: 2020-03-03
Modeling | (prelim) Multivariate time series modeling (VAR) with likely features | bar: 2020-03-04 to 2020-03-10
Data Acquisition: Base Features | note WHY features are likely based on domain knowledge | bar: 2020-03-03 to 2020-03-05
Data Acquisition: Add'l Features | bar: 2020-03-05 to 2020-03-09
EDA: Base Features | bar: 2020-03-04 to 2020-03-06
EDA: Add'l Features | bar: 2020-03-07 to 2020-03-09
Feature Selection | based on multivariate models created in Modeling | bar: 2020-03-06 to 2020-03-10